## ProjectSchedule
XÂY DỰNG WEBSITE MORII COFFEE
| Enter Company Name in cell B2. | Company Name
| Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Project Lead | Project Start: | 2022-12-18
| The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: | 1899-12-31 |  |  |  | 2022-12-19 | [6 empty] | 2022-12-26 | [6 empty] | 2023-01-02 | [6 empty] | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-12-19 to 2023-03-19
| No. | TASK | ASSIGNED TO | START | END | DAYS | S | time axis 2022-12-19 to 2023-03-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
| 1 | Khởi động dự án | Nhung, Ánh, Tín, Long | 2022-09-22 | 2022-09-28 | bar: 2022-12-19 to 2022-12-30
| 1.1 | Lập bản tuyên bố dự án | Nhung | 2022-09-22 | 2022-09-23
| 1.2 | Khảo sát | Nhung | 2022-09-23 | 2022-09-25
| 1.2.1 | Khảo sát sơ bộ | Nhung | 2022-09-23 | 2022-09-24 | bar: 2022-12-19 to 2022-12-20
| 1.2.1.1 | Tìm hiểu người dùng | Nhung | 2022-09-23 | 2022-09-23 | bar: 2022-12-19 to 2022-12-20
| 1.2.1.2 | Tiìm hiểu doanh nghiệp | Nhung | 2022-09-23 | 2022-09-24 | bar: 2022-12-19 to 2022-12-20
| 1.2.2 | Khảo sát chi tiết | Nhung | 2022-09-24 | 2022-09-25
| 1.2.2.1 | Thu thập thông tin chi tiết của hệ thống | Nhung | 2022-09-24 | 2022-09-24 | bar: 2022-12-21 to 2022-12-25
| 1.2.2.2 | Tìm hiểu chức năng xử lý hệ thống | Nhung | 2022-09-24 | 2022-09-24 | bar: 2022-12-21 to 2022-12-25
| 1.2.2.3 | Giao diện cơ bản | Nhung | 2022-09-24 | 2022-09-25 | bar: 2022-12-21 to 2022-12-25
| 1.2.2.4 | Nghiệp vụ hệ thống | Nhung | 2022-09-25 | 2022-09-25 | bar: 2022-12-21 to 2022-12-25
| 1.3 | Lập kế hoạch | Long, Ánh, Tín | 2022-09-25 | 2022-09-28
| 1.3.1 | Kế khoạch thiết kế giao diện | Long | 2022-09-25 | 2022-09-26 | bar: 2022-12-21 to 2022-12-22
| 1.3.2 | Kế hoạch phát triển tính năng | Tín | 2022-09-26 | 2022-09-27 | bar: 2022-12-23 to 2022-12-24
| 1.3.3 | Kế hoạch kiểm thử | Ánh | 2022-09-27 | 2022-09-28 | bar: 2022-12-25 to 2022-12-29
| 1.3.4 | Kế hoạch quản lý phạm vi | Ánh, Tín | 2022-09-28 | 2022-09-28 | bar: 2022-12-25 to 2022-12-29
| 2 | Phân tích hệ thống và lấy yêu cầu | Nhung, Ánh, Tín, Long | 2022-09-28 | 2022-10-04 | bar: 2022-12-31 to 2023-01-12
| 2.1 | Xác định mục tiêu và phạm vi | Nhung, Tín | 2022-09-28 | 2022-09-29 | bar: 2022-12-31 to 2023-01-01
| 2.2 | Mô tả nghiệp vụ và qui trình cho dự án | Nhung, Ánh, Tín, Long | 2022-09-29 | 2022-10-02
| 2.2.1 | Quy trình cho khách hàng | Tín | 2022-09-29 | 2022-09-30 | bar: 2023-01-07 to 2023-01-09
| 2.2.2 | Quy trình cho nhân viên | Ánh | 2022-09-30 | 2022-10-01 | bar: 2023-01-07 to 2023-01-09
| 2.2.3 | Quy trình cho quản lý | Nhung, Long | 2022-10-01 | 2022-10-02 | bar: 2023-01-07 to 2023-01-09
| 2.3 | Xác định yêu cầu | Ánh, Long | 2022-10-02 | 2022-10-04
| 2.3.1 | Yêu cầu chức năng | Ánh | 2022-10-02 | 2022-10-03 | bar: 2023-01-03 to 2023-01-05
| 2.3.2 | Yêu cầu phi chức năng | Long | 2022-10-03 | 2022-10-04 | bar: 2023-01-03 to 2023-01-05
| 3 | Thiết kế lược đồ Cơ sở dữ liệu | Nhung, Ánh, Tín, Long | 2022-10-04 | 2022-10-22 | bar: 2023-01-10 to 2023-01-23
| 3.1 | Xây dựng mô hình | Ánh, Tín, Long | 2022-10-04 | 2022-10-04
| 3.1.1 | Xây dựng mô hình thực thể kết hợp | Ánh | 2022-10-04 | 2022-10-04 | bar: 2023-01-10 to 2023-01-12
| 3.1.2 | Xây dựng mô hình dữ liệu quan hệ | Long | 2022-10-04 | 2022-10-04 | bar: 2023-01-10 to 2023-01-12
| 3.1.3 | Viết quy định hệ thống | Tín | 2022-10-04 | 2022-10-04 | bar: 2023-01-10 to 2023-01-12
| 3.2 | Lập sơ đồ Use case và đặc tả Use case | Nhung, Ánh, Tín, Long | 2022-10-04 | 2022-10-18
| 3.2.1 | Use case Đăng nhập | Tín | 2022-10-04 | 2022-10-04
| 3.2.2 | Use case Đăng ký | Tín | 2022-10-04 | 2022-10-04 | bar: 2023-01-13 to 2023-01-20
| 3.2.3 | Use case Xem thông tin cá nhân | Tín | 2022-10-04 | 2022-10-05 | bar: 2023-01-13
| 3.2.3.1 | Use case Sửa thông tin cá nhân | Tín | 2022-10-04 | 2022-10-04 | bar: 2023-01-13
| 3.2.3.2 | Use case Đổi mật khẩu | Tín | 2022-10-04 | 2022-10-05 | bar: 2023-01-13 to 2023-01-20
| 3.2.4 | Use case Quên mật khẩu | Ánh | 2022-10-05 | 2022-10-05 | bar: 2023-01-13 to 2023-01-20
| 3.2.5 | Use case Quản lý thông tin nhân viên | Ánh | 2022-10-05 | 2022-10-07 | bar: 2023-01-13 to 2023-01-20
| 3.2.5.1 | Use case Thêm thông tin nhân viên | Ánh | 2022-10-05 | 2022-10-05 | bar: 2023-01-13 to 2023-01-20
| 3.2.5.2 | Use case Xóa thông tin nhân viên | Ánh | 2022-10-05 | 2022-10-05 | bar: 2023-01-13 to 2023-01-20
| 3.2.5.3 | Use case Sửa thông tin nhân viên | Ánh | 2022-10-05 | 2022-10-06 | bar: 2023-01-13 to 2023-01-20
| 3.2.5.4 | Use case Tra cứu thông tin nhân viên | Ánh | 2022-10-06 | 2022-10-07 | bar: 2023-01-13 to 2023-01-20
| 3.2.5.5 | Use case Xem thông tin nhân viên | Ánh | 2022-10-07 | 2022-10-07 | bar: 2023-01-13 to 2023-01-20
| 3.2.6 | Use case Quản lý thông tin khách hàng | Tín | 2022-10-07 | 2022-10-08 | bar: 2023-01-13 to 2023-01-20
| 3.2.6.1 | Use case Thêm Khách hàng | Tín | 2022-10-07 | 2022-10-08 | bar: 2023-01-13 to 2023-01-20
| 3.2.6.2 | Use case Tra cứu thông tin khách hàng | Tín | 2022-10-08 | 2022-10-08 | bar: 2023-01-13 to 2023-01-20
| 3.2.6.3 | Use case Xem thông tin khách hàng | Tín | 2022-10-08 | 2022-10-08 | bar: 2023-01-13 to 2023-01-20
| 3.2.7 | Use case Quản lý thông tin sản phẩm | Nhung | 2022-10-08 | 2022-10-10 | bar: 2023-01-13 to 2023-01-20
| 3.2.7.1 | Use case Thêm sản phẩm | Nhung | 2022-10-08 | 2022-10-08 | bar: 2023-01-13 to 2023-01-20
| 3.2.7.2 | Use case Xóa sản phẩm | Nhung | 2022-10-08 | 2022-10-09 | bar: 2023-01-13 to 2023-01-20
| 3.2.7.3 | Use case Sửa thông tin sản phẩm | Nhung | 2022-10-09 | 2022-10-09 | bar: 2023-01-13 to 2023-01-20
| 3.2.7.4 | Use case Tra cứu sản phẩm | Nhung | 2022-10-10 | 2022-10-10 | bar: 2023-01-13
| 3.2.7.5 | Use case Xem sản phẩm | Nhung | 2022-10-10 | 2022-10-10 | bar: 2023-01-13
| 3.2.8 | Use case Quản lý Blog | Ánh | 2022-10-10 | 2022-10-12 | bar: 2023-01-13
| 3.2.8.1 | Use case Tạo blog | Ánh | 2022-10-10 | 2022-10-10 | bar: 2023-01-13
| 3.2.8.2 | Use case Sửa blog | Ánh | 2022-10-10 | 2022-10-11 | bar: 2023-01-13
| 3.2.8.3 | Use case Xóa blog | Ánh | 2022-10-11 | 2022-10-12 | bar: 2023-01-13
| 3.2.8.4 | Use case Tra cứu blog | Ánh | 2022-10-12 | 2022-10-12 | bar: 2023-01-13
| 3.2.8.5 | Use case Xem blog | Ánh | 2022-10-12 | 2022-10-12 | bar: 2023-01-13
| 3.2.9 | Use Quản lý thông tin khuyến mãi | Nhung | 2022-10-12 | 2022-10-13 | bar: 2023-01-13
| 3.2.9.1 | Use case Xem thông tin khuyến mãi | Nhung | 2022-10-12 | 2022-10-12 | bar: 2023-01-13
| 3.2.9.2 | Use case Thêm thông tin khuyến mãi | Nhung | 2022-10-12 | 2022-10-13 | bar: 2023-01-13
| 3.2.9.3 | Use case Xóa thông tin khuyến mãi | Nhung | 2022-10-13 | 2022-10-13 | bar: 2023-01-13
| 3.2.9.4 | Use case Sửa thông tin khuyến mãi | Nhung | 2022-10-13 | 2022-10-13 | bar: 2023-01-13
khách hàng | 3.2.10 | Use case Báo cáo thống kê | Long | 2022-10-13 | 2022-10-13 | bar: 2023-01-13
| 3.2.11 | Use case Quản lý thông tin hóa đơn | Nhung | 2022-10-13 | 2022-10-15 | bar: 2023-01-13 to 2023-01-20
| 3.2.1.1 | Use case Thêm hóa đơn | Nhung | 2022-10-13 | 2022-10-13 | bar: 2023-01-13 to 2023-01-20
| 3.2.1.2 | Use case Xem hóa đơn | Nhung | 2022-10-13 | 2022-10-13 | bar: 2023-01-13
| 3.2.1.3 | Use case Thanh toán hóa đơn | Nhung | 2022-10-14 | 2022-10-14 | bar: 2023-01-13
| 3.2.1.4 | Use case Tra cứu hóa đơn | Nhung | 2022-10-14 | 2022-10-15 | bar: 2023-01-13
| 3.2.12 | Use case Quản lý thông tin đơn hàng | Nhung | 2022-10-15 | 2022-10-16 | bar: 2023-01-13 to 2023-01-20
| 3.2.12.1 | Use case Cập nhật tình trạng đơn hàng | Nhung | 2022-10-15 | 2022-10-15 | bar: 2023-01-13
| 3.2.12.2 | Use case Xem thông tin đơn hàng | Nhung | 2022-10-15 | 2022-10-16 | bar: 2023-01-13
| 3.2.12.3 | Use case Tra cứu thông tin đơn hàng | Nhung | 2022-10-16 | 2022-10-16 | bar: 2023-01-13
| 3.2.13 | Use case Giao hàng | Long | 2022-10-16 | 2022-10-16 | bar: 2023-01-13 to 2023-01-20
| 3.2.14 | Use case Xem câu chuyện | Nhung | 2022-10-17 | 2022-10-17 | bar: 2023-01-13 to 2023-01-20
| 3.2.15 | Use case Xem thông tin sản phẩm | Long | 2022-10-17 | 2022-10-17 | bar: 2023-01-13 to 2023-01-20
| 3.2.15.1 | Use case Tìm kiếm sản phẩm | Long | 2022-10-17 | 2022-10-17 | bar: 2023-01-13 to 2023-01-20
| 3.2.16 | Use case Đặt hàng | Ánh | 2022-10-17 | 2022-10-19 | bar: 2023-01-13
| 3.2.16.1 | Use case Hủy đơn hàng | Ánh | 2022-10-17 | 2022-10-18 | bar: 2023-01-13
| 3.2.16.2 | Use case Thanh toán | Ánh | 2022-10-18 | 2022-10-19 | bar: 2023-01-13
| 3.2.17 | Use case Quản lý giỏ hàng | Ánh | 2022-10-19 | 2022-10-20 | bar: 2023-01-13
| 3.2.17.1 | Use case Xóa sản phẩm trong giỏ hàng | Ánh | 2022-10-19 | 2022-10-19 | bar: 2023-01-13
| 3.2.17.2 | Use case Sửa sản phẩm trong giỏ hàng | Ánh | 2022-10-19 | 2022-10-19 | bar: 2023-01-13
| 3.2.17.3 | Use case Thêm sản phẩm vào giỏ hàng | Ánh | 2022-10-19 | 2022-10-19 | bar: 2023-01-13
| 3.2.18 | Use case Tra cứu đơn đã đặt | Long | 2022-10-19 | 2022-10-20 | bar: 2023-01-13
| 3.2.19 | Use case Xem blog | Long | 2022-10-20 | 2022-10-21 | bar: 2023-01-13
| 3.2.20 | Use case Xem lịch sử đặt hàng | Long | 2022-10-21 | 2022-10-21 | bar: 2023-01-13
| 3.3 | Thiết lập ràng buộc cho Cơ sở dữ liệu | Long, Tín | 2022-10-21 | 2022-10-22 | bar: 2023-01-20 to 2023-01-21
| 3.3.1 | Ràng buộc khóa chính | Long | 2022-10-21 | 2022-10-22 | bar: 2023-01-21 to 2023-01-22
| 3.3.1.1 | Ràng buộc khóa chính bảng Nhân viên | Long | 2022-10-21 | 2022-10-21 | bar: 2023-01-22 to 2023-01-23
| 3.3.1.2 | Ràng buộc khóa chính bảng Khách hàng | Long | 2022-10-21 | 2022-10-21 | bar: 2023-01-22
| 3.3.1.3 | Ràng buộc khóa chính bảng Người dùng | Long | 2022-10-21 | 2022-10-21 | bar: 2023-01-22
| 3.3.1.4 | Ràng buộc khóa chính bảng Quản lý | Long | 2022-10-21 | 2022-10-21 | bar: 2023-01-22
| 3.3.1.5 | Ràng buộc khóa chính bảng Sản phẩm | Long | 2022-10-21 | 2022-10-21 | bar: 2023-01-22
| 3.3.1.6 | Ràng buộc khóa chính bảng Khuyến mãi | Long | 2022-10-21 | 2022-10-22 | bar: 2023-01-22
| 3.3.1.7 | Ràng buộc khóa chính bảng Hóa đơn | Long | 2022-10-22 | 2022-10-22 | bar: 2023-01-22
| 3.3.1.8 | Ràng buộc khóa chính bảng Chi tiết hóa đơn | Long | 2022-10-22 | 2022-10-22 | bar: 2023-01-22
| 3.3.1.9 | Ràng buộc khóa chính bảng Cửa hàng | Long | 2022-10-22 | 2022-10-22 | bar: 2023-01-22
| 3.3.1.10 | Ràng buộc khóa chính bảng Đặt hàng | Long | 2022-10-22 | 2022-10-22 | bar: 2023-01-22
| 3.3.1.11 | Ràng buộc khóa chính bảng Phân Loại | Long | 2022-10-22 | 2022-10-22 | bar: 2023-01-22
| 3.3.2 | Ràng buộc khóa ngoại | Tín | 2022-10-22 | 2022-10-23
| 3.3.2.1 | Ràng buộc khóa ngoại bảng Người dùng | Tín | 2022-10-22 | 2022-10-22
| 3.3.2.2 | Ràng buộc khóa ngoại bảng Khách hàng | Tín | 2022-10-22 | 2022-10-22
| 3.3.2.3 | Ràng buộc khóa ngoại bảng Nhân viên | Tín | 2022-10-22 | 2022-10-22
| 3.3.2.4 | Ràng buộc khóa ngoại bảng Quản lý | Tín | 2022-10-22 | 2022-10-22
| 3.3.2.5 | Ràng buộc khóa ngoại bảng Sản phẩm | Tín | 2022-10-22 | 2022-10-22
| 3.3.2.6 | Ràng buộc khóa ngoại bảng Khuyến mãi | Tín | 2022-10-22 | 2022-10-23
| 3.3.2.7 | Ràng buộc khóa ngoại bảng Hóa đơn | Tín | 2022-10-23 | 2022-10-23
| 3.3.2.8 | Ràng buộc khóa ngoại bảng Chi tiết hóa đơn | Tín | 2022-10-23 | 2022-10-23
| 3.3.2.9 | Ràng buộc khóa ngoại bảng Cửa hàng | Tín | 2022-10-23 | 2022-10-23
| 3.3.2.10 | Ràng buộc khóa chính bảng Đặt hàng | Tín | 2022-10-23 | 2022-10-23 | bar: 2023-01-22
| 3.3.2.11 | Ràng buộc khóa chính bảng Phân Loại | Tín | 2022-10-23 | 2022-10-23 | bar: 2023-01-22
| 4 | Thiết kế giao diện người dùng | Nhung, Ánh, Tín, Long | 2022-10-23 | 2022-11-05 | bar: 2023-01-24 to 2023-02-14
| 4.1 | Khảo sát giao diện | Nhung | 2022-10-23 | 2022-10-23
| 4.1.1 | Khảo sát các giao diện website tương tự | Nhung | 2022-10-23 | 2022-10-23 | bar: 2023-01-24 to 2023-01-28
| 4.1.2 | Khảo sát giao diện từ nhu cầu người dùng | Nhung | 2022-10-23 | 2022-10-23 | bar: 2023-01-24 to 2023-01-28
| 4.2 | Thiết kế giao diện | Nhung, Ánh, Tín, Long | 2022-10-23 | 2022-11-03
| 4.2.1 | Thiết kế giao diện Đăng ký | Tín | 2022-10-23 | 2022-10-23 | bar: 2023-01-29 to 2023-02-06
| 4.2.2 | Thiết kế giao diện Đăng nhập | Tín | 2022-10-23 | 2022-10-23 | bar: 2023-01-29 to 2023-02-06
| 4.2.3 | Thiết kế giao diện Quên mật khẩu | Ánh | 2022-10-23 | 2022-10-23 | bar: 2023-01-29 to 2023-02-06
| 4.2.4 | Thiết kế giao diện Xem thông tin cá nhân | Tín | 2022-10-23 | 2022-10-23 | bar: 2023-01-29 to 2023-02-06
| 4.2.4.1 | Thiết kế giao diện Sửa thông tin cá nhân | Tín | 2022-10-23 | 2022-10-23 | bar: 2023-01-29 to 2023-02-06
| 4.2.4.2 | Thiết kế giao diện Đổi mật khẩu | Tín | 2022-10-23 | 2022-10-23 | bar: 2023-01-29 to 2023-02-06
| 4.2.5 | Thiết kế giao diện Quản lý thông tin nhân viên | Ánh | 2022-10-23 | 2022-10-24 | bar: 2023-01-29 to 2023-02-06
| 4.2.5.1 | Thiết kế giao diện Thêm thông tin nhân viên | Ánh | 2022-10-23 | 2022-10-23 | bar: 2023-01-29 to 2023-02-06
| 4.2.5.2 | Thiết kế giao diện Xóa thông tin nhân viên | Ánh | 2022-10-23 | 2022-10-23 | bar: 2023-01-29 to 2023-02-06
| 4.2.5.3 | Thiết kế giao diện Sửa thông tin nhân viên | Ánh | 2022-10-23 | 2022-10-24 | bar: 2023-01-29 to 2023-02-06
| 4.2.5.4 | Thiết kế giao diện Tra cứu thông tin nhân viên | Ánh | 2022-10-24 | 2022-10-24 | bar: 2023-01-29 to 2023-02-06
| 4.2.5.5 | Thiết kế giao diện Xem thông tin nhân viên | Ánh | 2022-10-24 | 2022-10-24 | bar: 2023-01-29 to 2023-02-06
| 4.2.6 | Thiết kế giao diện Quản lý khách hàng | Tín | 2022-10-24 | 2022-10-25 | bar: 2023-01-29
| 4.2.6.1 | Thiết kế giao diện Thêm khách hàng | Tín | 2022-10-24 | 2022-10-24 | bar: 2023-01-29
| 4.2.6.2 | Thiết kế giao diện Tìm kiếm thông tin khách hàng | Tín | 2022-10-24 | 2022-10-25 | bar: 2023-01-29
| 4.2.6.3 | Thiết kế giao diện Xem thông tin khách hàng | Tín | 2022-10-25 | 2022-10-25 | bar: 2023-01-29
| 4.2.7 | Thiết kế giao diện Quản lý thông tin sản phẩm | Nhung | 2022-10-25 | 2022-10-26 | bar: 2023-01-29
| 4.2.7.1 | Thiết kế giao diện Thêm sản phẩm | Nhung | 2022-10-25 | 2022-10-25 | bar: 2023-01-29
| 4.2.7.2 | Thiết kế giao diện Xóa sản phẩm | Nhung | 2022-10-25 | 2022-10-25 | bar: 2023-01-29
| 4.2.7.3 | Thiết kế giao diện Sửa thông tin sản phẩm | Nhung | 2022-10-25 | 2022-10-26 | bar: 2023-01-29
| 4.2.7.4 | Thiết kế giao diện Tìm kiếm sản phẩm | Nhung | 2022-10-26 | 2022-10-26 | bar: 2023-01-29
| 4.2.7.5 | Thiết kế giao diện Xem sản phẩm | Nhung | 2022-10-26 | 2022-10-26 | bar: 2023-01-29
| 4.2.8 | Thiết kế giao diện Quản lý blog | Ánh | 2022-10-26 | 2022-10-27 | bar: 2023-01-29
| 4.2.8.1 | Thiết kế giao diện Tạo blog | Ánh | 2022-10-26 | 2022-10-26 | bar: 2023-01-29
| 4.2.8.2 | Thiết kế giao diện Sửa blog | Ánh | 2022-10-26 | 2022-10-26 | bar: 2023-01-29
| 4.2.8.3 | Thiết kế giao diện Xóa blog | Ánh | 2022-10-26 | 2022-10-27 | bar: 2023-01-29
| 4.2.8.4 | Thiết kế giao diện Tra cứu blog | Ánh | 2022-10-27 | 2022-10-27 | bar: 2023-01-29
| 4.2.9 | Thiết kế giao diện Quản lý thông tin khuyến mãi | Nhung | 2022-10-27 | 2022-10-28 | bar: 2023-01-29
| 4.2.9.1 | Thiết kế giao diện Xem thông tin khuyến mãi | Nhung | 2022-10-27 | 2022-10-27 | bar: 2023-01-29
| 4.2.9.2 | Thiết kế giao diện Thêm thông tin khuyến mãi | Nhung | 2022-10-27 | 2022-10-27 | bar: 2023-01-29
| 4.2.9.3 | Thiết kế giao diện Xóa thông tin khuyến mãi | Nhung | 2022-10-28 | 2022-10-28 | bar: 2023-01-29
| 4.2.9.4 | Thiết kế giao diện Sửa thông tin khuyến mãi | Nhung | 2022-10-28 | 2022-10-28 | bar: 2023-01-29
| 4.2.10 | Thiết kế giao diện Báo cáo thống kê | Long | 2022-10-28 | 2022-10-29 | bar: 2023-01-29
| 4.2.11 | Thiết kế giao diện Quản lý thông tin hóa đơn | Long | 2022-10-29 | 2022-10-30 | bar: 2023-01-29
| 4.2.11.1 | Thiết kế giao diện Thêm hóa đơn | Long | 2022-10-29 | 2022-10-29 | bar: 2023-01-29
| 4.2.11.2 | Thiết kế giao diện Xem hóa đơn | Long | 2022-10-29 | 2022-10-29 | bar: 2023-01-29
| 4.2.11.3 | Thiết kế giao diện Thanh toán hóa đơn | Long | 2022-10-29 | 2022-10-30 | bar: 2023-01-29
| 4.2.11.4 | Thiết kế giao diện Tra cứu hóa đơn | Long | 2022-10-30 | 2022-10-30 | bar: 2023-01-29
| 4.2.12 | Thiết kế giao diện Quản lý thông tin đơn hàng | Long | 2022-10-30 | 2022-10-31 | bar: 2023-01-29
| 4.2.12.1 | Thiết kế giao diện Cập nhật tình trạng đơn hàng | Long | 2022-10-30 | 2022-10-31 | bar: 2023-01-29
| 4.2.12.2 | Thiết kế giao diện Xem thông tin đơn hàng | Long | 2022-10-31 | 2022-10-31 | bar: 2023-01-29
| 4.2.12.3 | Thiết kế giao diện Tra cứu thông tin đơn hàng | Long | 2022-10-31 | 2022-10-31 | bar: 2023-01-29
| 4.2.13 | Thiết kế giao diện Xem câu chuyện | Nhung | 2022-10-31 | 2022-10-31 | bar: 2023-01-29
| 4.2.14 | Thiết kế giao diện Xem thông tin sản phẩm | Nhung | 2022-10-31 | 2022-10-31 | bar: 2023-01-29
| 4.2.14.1 | Thiết kế giao diện Tìm kiếm sản phẩm | Nhung | 2022-10-31 | 2022-10-31 | bar: 2023-01-29
| 4.2.15 | Thiết kế giao diện Đặt hàng | Long | 2022-10-31 | 2022-11-01 | bar: 2023-01-29
| 4.2.15.1 | Thiết kế giao diện Hủy đơn hàng | Long | 2022-10-31 | 2022-10-31 | bar: 2023-01-29
| 4.2.15.2 | Thiết kế giao diện Thanh toán | Long | 2022-10-31 | 2022-11-01 | bar: 2023-01-29
| 4.2.16 | Thiết kế giao diện Quản lý giỏ hàng | Long | 2022-11-01 | 2022-11-01 | bar: 2023-01-29
| 4.2.16.1 | Thiết kế giao diện Thêm sản phẩm vào giỏ hàng | Long | 2022-11-01 | 2022-11-01 | bar: 2023-01-29
| 4.2.16.2 | Thiết kế giao diện Xóa sản phẩm trong giỏ hàng | Long | 2022-11-01 | 2022-11-01 | bar: 2023-01-29
| 4.2.16.3 | Thiết kế giao diện Sửa sản phẩm trong giỏ hàng | Long | 2022-11-01 | 2022-11-01 | bar: 2023-01-29
| 4.2.17 | Thiết kế giao diện Thanh toán | Long | 2022-11-01 | 2022-11-01 | bar: 2023-01-29
| 4.2.18 | Thiết kế giao diện Tra cứu đơn đã đặt | Long | 2022-11-01 | 2022-11-01 | bar: 2023-01-29
| 4.2.19 | Thiết kế giao diện Xem blog | Ánh | 2022-11-02 | 2022-11-02 | bar: 2023-01-29
| 4.2.20 | Thiết kế giao diện Xem lịch sử đặt hàng | Long | 2022-11-02 | 2022-11-03 | bar: 2023-01-29
| 4.2.21 | Thiết kế giao diện Trang chủ | Nhung, Long | 2022-11-03 | 2022-11-03 | bar: 2023-01-29
| 4.2.22 | Thiết kế giao diện Liên hệ | Ánh | 2022-11-03 | 2022-11-03 | bar: 2023-01-29
| 4.3 | Phát triển các tính năng | Nhung, Ánh, Tín, Long | 2022-11-03 | 2022-11-05
| 4.3.1 | Tính năng Liên hệ | Ánh | 2022-11-03 | 2022-11-03 | bar: 2023-02-07 to 2023-02-09
| 4.3.2 | Tính năng Tùy biến | Tín | 2022-11-03 | 2022-11-03 | bar: 2023-02-10 to 2023-02-12
| 4.3.3 | Tính năng Xây dựng blog | Ánh | 2022-11-03 | 2022-11-03 | bar: 2023-02-07
| 4.3.4 | Tính năng Tìm kiếm thông tin | Tín | 2022-11-03 | 2022-11-03 | bar: 2023-02-08 to 2023-02-10
| 4.3.5 | Tính năng Giỏ hàng | Long | 2022-11-03 | 2022-11-04 | bar: 2023-02-07 to 2023-02-12
| 4.3.6 | Tính năng Giao hàng | Tín | 2022-11-04 | 2022-11-04 | bar: 2023-02-07 to 2023-02-10
| 4.3.7 | Tính năng Quản lý đơn hàng | Ánh | 2022-11-04 | 2022-11-04 | bar: 2023-02-11 to 2023-02-12
| 4.3.8 | Tính năng Quản lý khách hàng | Nhung | 2022-11-04 | 2022-11-05 | bar: 2023-02-11 to 2023-02-12
| 4.3.9 | Tính năng Quản lý sản phẩm | Nhung | 2022-11-05 | 2022-11-05 | bar: 2023-02-11 to 2023-02-12
| 4.3.10 | Tính năng Hỗ trợ tiếp thị | Tín | 2022-11-05 | 2022-11-05 | bar: 2023-02-11 to 2023-02-12
| 4.3.11 | Tính năng phân quyền | Long | 2022-11-05 | 2022-11-05 | bar: 2023-02-11 to 2023-02-12
| 4.4 | Kiểm tra chỉnh sửa các giao diện | Nhung, Ánh, Tín, Long | 2022-11-05 | 2022-11-05
| 5 | Phát triển dự án | Nhung, Ánh, Tín, Long | 2022-11-05 | 2022-12-07
| 5.1 | Xây dựng cơ sở dữ liệu | Long, Tín | 2022-11-05 | 2022-11-07 | bar: 2023-02-07 to 2023-02-24
| 5.1.1 | Dữ liệu Nhân viên | Long | 2022-11-05 | 2022-11-05 | bar: 2023-02-07 to 2023-02-11
| 5.1.2 | Dữ liệu Khách hàng | Long | 2022-11-05 | 2022-11-05 | bar: 2023-02-07 to 2023-02-11
| 5.1.3 | Dữ liệu Người dùng | Long | 2022-11-05 | 2022-11-05 | bar: 2023-02-07 to 2023-02-11
| 5.1.4 | Dữ liệu Quản lý | Long | 2022-11-05 | 2022-11-05 | bar: 2023-02-07 to 2023-02-11
| 5.1.5 | Dữ liệu Sản phẩm | Long | 2022-11-05 | 2022-11-06 | bar: 2023-02-07 to 2023-02-11
| 5.1.6 | Dữ liệu Khuyến mãi | Tín | 2022-11-06 | 2022-11-06 | bar: 2023-02-07 to 2023-02-11
| 5.1.7 | Dữ liệu Hóa đơn | Tín | 2022-11-06 | 2022-11-06 | bar: 2023-02-07 to 2023-02-11
| 5.1.8 | Dữ liệu Chi tiết hóa đơn | Tín | 2022-11-06 | 2022-11-06 | bar: 2023-02-07 to 2023-02-11
| 5.1.9 | Dữ liệu Cửa hàng | Tín | 2022-11-06 | 2022-11-07 | bar: 2023-02-07 to 2023-02-11
| 5.1.10 | Dữ liệu Đặt hàng | Tín | 2022-11-07 | 2022-11-07 | bar: 2023-02-07 to 2023-02-11
| 5.1.11 | Dữ liệu Blog | Tín | 2022-11-07 | 2022-11-07 | bar: 2023-02-07 to 2023-02-11
| 5.1.12 | Dữ liệu Chi tiết sản phẩm | Tín | 2022-11-07 | 2022-11-07 | bar: 2023-02-07 to 2023-02-11
| 5.1.13 | Dữ liệu Phân Loại | Tín | 2022-11-07 | 2022-11-07 | bar: 2023-02-07 to 2023-02-11
| 5.2 | Lựa chọn công cụ thực hiện | Nhung, Ánh | 2022-11-07 | 2022-11-07
| 5.2.1 | Lựa chọn hệ quản trị cơ sở dữ liệu | Ánh | 2022-11-07 | 2022-11-07 | bar: 2023-02-07 to 2023-02-09
| 5.2.2 | Lựa chọn công cụ lập trình | Ánh, Nhung | 2022-11-07 | 2022-11-07 | bar: 2023-02-07 to 2023-02-09
| 5.2.3 | Lựa chọn công cụ phác thảo giao diện | Ánh | 2022-11-07 | 2022-11-07 | bar: 2023-02-07 to 2023-02-09
| 5.2.4 | Lựa chọn công cụ quản lý dự án | Nhung | 2022-11-07 | 2022-11-07 | bar: 2023-02-07
| 5.2.5 | Lựa chọn công cụ trình bày dự án | Nhung | 2022-11-07 | 2022-11-07 | bar: 2023-02-07
| 5.3 | Lập trình giao diện | Nhung, Ánh, Tín, Long | 2022-11-07 | 2022-11-17
| 5.3.1 | Giao diện Đăng nhập | Tín | 2022-11-07 | 2022-11-08 | bar: 2023-02-14 to 2023-02-19
| 5.3.2 | Giao diện Đăng ký | Tín | 2022-11-08 | 2022-11-09 | bar: 2023-02-14
| 5.3.3 | Giao diện Trang chủ | Nhung, Long | 2022-11-09 | 2022-11-10 | bar: 2023-02-14 to 2023-02-19
| 5.3.4 | Giao diện Đặt hàng | Long | 2022-11-10 | 2022-11-10 | bar: 2023-02-14 to 2023-02-19
| 5.3.5 | Giao diện Xem thông tin cá nhân | Tín | 2022-11-10 | 2022-11-10 | bar: 2023-02-14 to 2023-02-19
| 5.3.6 | Giao diện Quên mật khẩu | Ánh | 2022-11-10 | 2022-11-11 | bar: 2023-02-14 to 2023-02-19
| 5.3.7 | Giao diện Quản lý thông tin nhân viên | Ánh | 2022-11-11 | 2022-11-11 | bar: 2023-02-14 to 2023-02-19
| 5.3.8 | Giao diện Quản lý thông tin khách hàng | Tín | 2022-11-11 | 2022-11-12 | bar: 2023-02-14 to 2023-02-19
| 5.3.9 | Giao diện Quản lý thông tin sản phẩm | Nhung | 2022-11-12 | 2022-11-12 | bar: 2023-02-14
| 5.3.10 | Giao diện Quản lý blog | Ánh | 2022-11-12 | 2022-11-13 | bar: 2023-02-14
| 5.3.11 | Giao diện Quản lý thông tin khuyến mãi | Nhung | 2022-11-13 | 2022-11-13 | bar: 2023-02-14
| 5.3.12 | Giao diện Báo cáo thống kê | Long | 2022-11-13 | 2022-11-14 | bar: 2023-02-14
| 5.3.13 | Giao diện Quản lý thông tin hóa đơn | Long | 2022-11-14 | 2022-11-14 | bar: 2023-02-14
| 5.3.14 | Giao diện Quản lý thông tin đơn hàng | Long | 2022-11-14 | 2022-11-14 | bar: 2023-02-14
| 5.3.15 | Giao diện Xem câu chuyện | Nhung | 2022-11-14 | 2022-11-14 | bar: 2023-02-14
| 5.3.16 | Giao diện Xem thông tin sản phẩm | Nhung | 2022-11-14 | 2022-11-15 | bar: 2023-02-14
| 5.3.17 | Giao diện Thanh toán | Long | 2022-11-15 | 2022-11-16 | bar: 2023-02-14
| 5.3.18 | Giao diện Quản lý giỏ hàng | Long | 2022-11-16 | 2022-11-17 | bar: 2023-02-14
| 5.3.19 | Giao diện Xem lịch sử đặt hàng | Long | 2022-11-17 | 2022-11-17 | bar: 2023-02-14
| 5.3.20 | Giao diện Xem blog | Ánh | 2022-11-17 | 2022-11-17 | bar: 2023-02-14
| 5.3.21 | Giao diện Liên hệ | Ánh | 2022-11-17 | 2022-11-17 | bar: 2023-02-14
| 5.3.22 | Giao diện Đổi mật khẩu | Tín | 2022-11-17 | 2022-11-17 | bar: 2023-02-14
| 5.4 | Lập trình chức năng |  | 2022-11-17 | 2022-12-06 | bar: 2023-02-20 to 2023-02-22
| 5.4.1 | Chức năng Phân quyền | Long | 2022-11-17 | 2022-11-19 | bar: 2023-02-20 to 2023-02-22
| 5.4.2 | Chức năng Đăng nhập | Tín | 2022-11-19 | 2022-11-21 | bar: 2023-02-20 to 2023-02-22
| 5.4.3 | Chức năng Đăng ký | Tín | 2022-11-21 | 2022-11-22 | bar: 2023-02-20
| 5.4.4 | Chức năng Tìm kiếm thông tin | Nhung | 2022-11-22 | 2022-11-23 | bar: 2023-02-20 to 2023-02-22
| 5.4.5 | Chức năng Quản lý nhân viên | Ánh | 2022-11-23 | 2022-11-25 | bar: 2023-02-20 to 2023-02-22
| 5.4.6 | Chức năng Quản lý khách hàng | Nhung | 2022-11-25 | 2022-11-27 | bar: 2023-02-20 to 2023-02-22
| 5.4.7 | Chức năng Quản lý đơn hàng | Long | 2022-11-27 | 2022-12-01 | bar: 2023-02-20
| 5.4.8 | Chức năng Quản lý blog | Ánh | 2022-12-01 | 2022-12-02 | bar: 2023-02-20
| 5.4.9 | Chức năng Quản lý thông tin khuyến mãi | Nhung | 2022-12-02 | 2022-12-02 | bar: 2023-02-20
| 5.4.10 | Chức năng Giỏ hàng | Long | 2022-12-02 | 2022-12-02 | bar: 2023-02-20
| 5.4.11 | Chức năng Đặt hàng | Long | 2022-12-02 | 2022-12-05 | bar: 2023-02-20 to 2023-02-22
| 5.4.12 | Chức năng Giao hàng | Long | 2022-12-05 | 2022-12-05 | bar: 2023-02-20
| 5.4.13 | Chức năng Xem thông tin | Tín | 2022-12-05 | 2022-12-06 | bar: 2023-02-20 to 2023-02-22
| 5.4.14 | Chức năng Báo cáo thống kê | Long | 2022-12-06 | 2022-12-06 | bar: 2023-02-20 to 2023-02-22
| 5.4.15 | Chức năng Quên mật khẩu | Ánh | 2022-12-06 | 2022-12-06 | bar: 2023-02-20 to 2023-02-22
| 5.4.16 | Chức năng Đổi mật khẩu | Tín | 2022-12-06 | 2022-12-06 | bar: 2023-02-20 to 2023-02-22
| 5.5 | Tài liệu hướng dẫn sử dụng | Long | 2022-12-06 | 2022-12-07 | bar: 2023-02-23
| 6 | Kiểm thử | Nhung, Ánh, Tín, Long | 2022-12-07 | 2022-12-14 | bar: 2023-02-24 to 2023-03-07
| 6.1 | Lập kế hoạch kiểm thử | Nhung | 2022-12-07 | 2022-12-08 | bar: 2023-02-24
| 6.2 | Thiết kế kịch bản cho quy trình kiểm thử | Ánh | 2022-12-08 | 2022-12-14
| 6.2.1 | Thiết kế testcase kiểm thử | Nhung, Ánh, Tín, Long | 2022-12-08 | 2022-12-14
| 6.2.1.1 | Test case Đăng nhập | Tín | 2022-12-08 | 2022-12-08 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.2 | Test case Đăng ký | Tín | 2022-12-08 | 2022-12-08 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.3 | Test case Sửa thông tin cá nhân | Tín | 2022-12-08 | 2022-12-08 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.4 | Test case Đổi mật khẩu | Tín | 2022-12-08 | 2022-12-08 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.5 | Test case Thêm thông tin nhân viên | Ánh | 2022-12-08 | 2022-12-08 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.6 | Test case Sửa thông tin nhân viên | Ánh | 2022-12-08 | 2022-12-08 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.7 | Test case Xóa thông tin nhân viên | Ánh | 2022-12-08 | 2022-12-09 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.8 | Test case Tìm kiếm thông tin nhân viên | Ánh | 2022-12-09 | 2022-12-09 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.9 | Use case Thêm sản phẩm | Nhung | 2022-12-09 | 2022-12-09 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.10 | Use case Xóa sản phẩm | Nhung | 2022-12-09 | 2022-12-09 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.11 | Use case Sửa thông tin sản phẩm | Nhung | 2022-12-09 | 2022-12-09 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.12 | Use case Tìm kiếm sản phẩm | Nhung | 2022-12-09 | 2022-12-09 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.13 | Use case Tạo blog | Ánh | 2022-12-09 | 2022-12-10 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.14 | Use case Sửa blog | Ánh | 2022-12-10 | 2022-12-10 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.15 | Use case Tra cứu blog | Ánh | 2022-12-10 | 2022-12-10 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.16 | Use case Thêm thông tin khuyến mãi | Nhung | 2022-12-10 | 2022-12-10 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.17 | Use case Xóa thông tin khuyến mãi | Nhung | 2022-12-10 | 2022-12-10 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.18 | Use case Sửa thông tin khuyến mãi | Nhung | 2022-12-10 | 2022-12-10 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.19 | Use case Báo cáo thống kê | Long | 2022-12-10 | 2022-12-10 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.20 | Use case Thêm hóa đơn | Long | 2022-12-10 | 2022-12-11 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.21 | Use case Xuất hóa đơn | Long | 2022-12-11 | 2022-12-11 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.22 | Use case Thanh toán hóa đơn | Long | 2022-12-11 | 2022-12-11 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.23 | Use case Tra cứu hóa đơn | Long | 2022-12-11 | 2022-12-11 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.24 | Use case Cập nhật tình trạng đơn hàng | Long | 2022-12-11 | 2022-12-11 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.25 | Use case Tra cứu thông tin đơn hàng | Long | 2022-12-11 | 2022-12-11 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.26 | Use case Xem câu chuyện | Nhung | 2022-12-11 | 2022-12-12 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.27 | Use case Tìm kiếm sản phẩm | Tín | 2022-12-12 | 2022-12-12 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.28 | Use case Đặt hàng | Long | 2022-12-12 | 2022-12-12 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.29 | Use case Hủy đơn hàng | Long | 2022-12-12 | 2022-12-12 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.30 | Use case Xóa sản phẩm trong giỏ hàng | Long | 2022-12-12 | 2022-12-12 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.31 | Use case Sửa sản phẩm trong giỏ hàng | Long | 2022-12-12 | 2022-12-13 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.32 | Use case Thêm sản phẩm vào giỏ hàng | Long | 2022-12-13 | 2022-12-13 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.33 | Use case Thanh toán | Long | 2022-12-13 | 2022-12-13 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.34 | Use case Xem lịch sử đặt hàng | Long | 2022-12-13 | 2022-12-13 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.35 | Use case Xem thông tin đơn hàng | Tín | 2022-12-13 | 2022-12-13 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.36 | Use case Xem blog | Tín | 2022-12-13 | 2022-12-14 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.37 | Use case Xem thông tin khách hàng | Tín | 2022-12-14 | 2022-12-14 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.38 | Use case Thêm thông tin khách hàng | Tín | 2022-12-14 | 2022-12-14 | bar: 2023-02-25 to 2023-02-28
| 6.2.1.39 | Use case Tra cứu thông tin khách hàng | Tín | 2022-12-14 | 2022-12-14 | bar: 2023-02-25 to 2023-02-28
| 7 | Triển khai dự án | Nhung, Ánh, Tín, Long | 2022-12-14 | 2022-12-21 | bar: 2023-03-05
| 7.1 | Cài đặt phần mềm | Tín | 2022-12-14 | 2022-12-15 | bar: 2023-03-05
| 7.2 | Theo dõi và đánh giá | Nhung, Ánh | 2022-12-15 | 2022-12-16
| 7.2.1 | Đánh giá kế hoạch theo tuần | Ánh | 2022-12-15 | 2022-12-16 | bar: 2023-03-06
| 7.2.2 | Đánh giá website | Nhung | 2022-12-16 | 2022-12-16 | bar: 2023-03-06
| 7.3 | Kiểm tra lần cuối | Long, Tín | 2022-12-16 | 2022-12-18
| 7.3.1 | Kiểm tra website qua hệ thống | Long | 2022-12-16 | 2022-12-17 | bar: 2023-03-08
| 7.3.2 | Xử lý các trường hợp bị lỗi | Tín | 2022-12-18 | 2022-12-18 | bar: 2023-03-10 to 2023-03-12
| 7.4 | Bảo trì website | Tín | 2022-12-18 | 2022-12-21 | bar: 2023-03-17
Note on C22: nhung : Họp 1 chưa có Ánh: này có ở dưới phần 6 rồi
Note on C36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chưa có phân công trong họp 2
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chưa phân công trong họp 2
Note on C122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Chưa có trong họp 4
Note on C184: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ngoài tính năng phân quyền tất cả đều không có trong họp4
Note on C198: nhung : Xây dựng dữ liệu theo bảng
Note on C217: nhung : behance, wordpress
Note on C218: nhung : Trang chính
Note on C241: nhung : tính năng nào lập trình chức năng đó